RESEARCH PROJECT PLAN

Hinglish Sentiment Analysis: Benchmarking Classical ML vs Transformer Models

B.Tech Research Paper | Duration: 10 Weeks

# 1. Project Overview

This document outlines the complete plan for a publishable ML research paper comparing sentiment analysis approaches on Hinglish (Hindi-English code-mixed) text. The paper targets IEEE or Springer-level conferences/journals.

| Field | Details |
| --- | --- |
| Paper Title | Comparative Analysis of ML and Transformer Models for Hinglish Sentiment Analysis |
| Dataset | SemEval 2020 Task 9 — Hinglish Sentiment Dataset (~14,000 labeled tweets) |
| Models | Logistic Regression, SVM, LSTM, MuRIL (Google Multilingual BERT for Indian Languages) |
| Target Venue | IEEE INDICON / ICCES / Elsevier Expert Systems with Applications |
| Total Duration | 10 Weeks (Part-time alongside college) |

# 2. Research Contribution

What makes this paper publishable — your unique contribution:

- Systematic benchmark of 4 models (2 classical + 1 deep learning + 1 transformer) on Hinglish text

- First use of MuRIL (specifically trained on Indian languages) for this dataset, compared against general baselines

- Error analysis explaining WHY classical models fail on code-mixed text

- Reproducible pipeline with open-source code released on GitHub

# 3. Project File Structure

Organize your code exactly as below. Each file has one responsibility. This structure is what you show your professor and what goes on GitHub.

| File / Folder | Purpose |
| --- | --- |
| data/raw/ | Original downloaded dataset files (do not modify) |
| data/processed/ | Cleaned and tokenized data saved as CSV |
| notebooks/EDA.ipynb | Exploratory data analysis — class distribution, word clouds, tweet length plots |
| src/preprocess.py | Text cleaning: remove URLs, normalize Devanagari/Roman mixing, lowercase |
| src/features.py | TF-IDF vectorizer for classical models; HuggingFace tokenizer for transformer |
| src/models/classical.py | Logistic Regression + SVM training using scikit-learn |
| src/models/lstm_model.py | Keras/PyTorch LSTM with Embedding layer and early stopping |
| src/models/transformer_model.py | MuRIL fine-tuning via HuggingFace Trainer API |
| src/train.py | Unified training entry point — call any model from here |
| src/evaluate.py | Metrics (Accuracy, F1, Precision, Recall), confusion matrices, result charts |
| results/ | Saved model checkpoints, evaluation JSON, plots for the paper |
| paper/ | LaTeX or Word draft of your paper |
| requirements.txt | All Python dependencies pinned to exact versions |

# 4. Code Flow — Step by Step

Follow this exact order when building the project. Each step produces an output that the next step consumes.

## Step 1 — Data Preprocessing (preprocess.py)

- Input: Raw CSV from SemEval 2020 Task 9

- Remove URLs, @mentions, hashtags, special characters

- Normalize mixed Devanagari-Roman characters

- Lowercase all text, strip extra whitespace

- Output: Clean CSV saved to data/processed/clean_data.csv

## Step 2 — Exploratory Data Analysis (EDA.ipynb)

- Plot class distribution (positive / negative / neutral counts)

- Plot tweet length histogram

- Generate word cloud for each sentiment class

- Output: Figures saved to results/ — these become figures in your paper

## Step 3 — Feature Extraction (features.py)

- For classical models: fit TF-IDF vectorizer, save fitted vectorizer with joblib

- For LSTM: build vocabulary index, convert text to padded integer sequences

- For transformer: use AutoTokenizer from HuggingFace (google/muril-base-cased)

- Do an 80/10/10 train/val/test split and keep it fixed for all models

## Step 4 — Classical Models (classical.py)

- Train Logistic Regression with TF-IDF features using sklearn

- Train SVM (LinearSVC) with same features

- Evaluate on test set, save Accuracy, F1-macro, Precision, Recall to results/metrics.json

## Step 5 — LSTM Model (lstm_model.py)

- Build: Embedding Layer -> LSTM Layer (128 units) -> Dropout -> Dense (3 classes, softmax)

- Train with Adam optimizer, categorical cross-entropy loss

- Use early stopping (patience=3) to prevent overfitting

- Save best model checkpoint, evaluate on test set, append metrics to results/metrics.json

## Step 6 — Transformer Fine-tuning (transformer_model.py)

- Load: google/muril-base-cased from HuggingFace

- Add classification head for 3 output classes

- Fine-tune for 3-5 epochs, learning rate 2e-5, batch size 16

- Use HuggingFace Trainer API with evaluation at each epoch

- Save best checkpoint, evaluate on test set, append metrics to results/metrics.json

## Step 7 — Evaluation and Visualization (evaluate.py)

- Load all metrics from results/metrics.json

- Generate comparison table: all 4 models x 4 metrics

- Plot confusion matrix for each model side by side

- Plot bar chart comparing F1 scores across models

- Output: All plots as PNG in results/ — directly usable in your paper

# 5. Week-by-Week Timeline

Estimated at 8-10 hours per week alongside college. Show this to your professor at your first meeting.

| Week | Phase | Tasks | Deliverable |
| --- | --- | --- | --- |
| 1 | Setup & Literature Review | Read 8-10 existing papers on Hinglish NLP and sentiment analysis. Download and explore dataset. Set up Python environment and GitHub repo. | Annotated paper list + repo created |
| 2 | Data Understanding | Run EDA notebook. Understand class imbalance. Plot all figures. Decide on preprocessing rules for your specific dataset. | EDA notebook complete, figures saved |
| 3 | Preprocessing | Write preprocess.py. Test on sample rows. Validate output. Handle edge cases like emoji, transliteration inconsistencies. | Clean dataset CSV ready |
| 4 | Classical Models | Build features.py (TF-IDF). Train Logistic Regression and SVM. Record baseline metrics. These are your comparison baselines. | Baseline results in metrics.json |
| 5 | LSTM Model | Build and train LSTM. Tune embedding size and LSTM units. Run with early stopping. Document hyperparameters used. | LSTM results added to metrics.json |
| 6 | Transformer (MuRIL) | Fine-tune MuRIL. This requires GPU — use Google Colab free tier if needed. Monitor training loss. Save best checkpoint. | MuRIL results, model checkpoint saved |
| 7 | Evaluation | Run evaluate.py. Generate all comparison tables, confusion matrices, bar charts. Perform error analysis — look at cases where best model fails. | All figures and tables for paper ready |
| 8 | Paper Writing | Write paper: Abstract, Introduction, Related Work, Methodology, Experiments, Results, Conclusion. Follow IEEE or Springer template exactly. | First complete draft |
| 9 | Professor Review | Share draft with professor. Incorporate feedback. Revise experiments if needed. Strengthen related work section. | Revised draft |
| 10 | Submission | Final proofreading. Format according to target venue guidelines. Upload to submission portal. Release code on GitHub. | Paper submitted |

# 6. Libraries and Tools Required

| Library | Purpose | Install Command |
| --- | --- | --- |
| pandas, numpy | Data loading, manipulation, and preprocessing | pip install pandas numpy |
| scikit-learn | TF-IDF, Logistic Regression, SVM, metrics | pip install scikit-learn |
| tensorflow / keras | LSTM model building and training | pip install tensorflow |
| transformers | MuRIL tokenizer and model, Trainer API | pip install transformers |
| torch | PyTorch backend for transformer fine-tuning | pip install torch |
| matplotlib, seaborn | Confusion matrices, bar charts, all figures | pip install matplotlib seaborn |
| Google Colab | Free GPU for MuRIL fine-tuning (Week 6) | colab.research.google.com |

# 7. Paper Structure (What to Write)

Follow this structure exactly. IEEE and Springer both use this format.

- Abstract (150-250 words): Problem, what you did, key result (e.g. MuRIL achieves 87% F1, outperforming SVM baseline by 12%)

- Introduction: Why Hinglish is hard for NLP, why this comparison matters, your contributions (3 bullet points)

- Related Work: Summarize 8-10 papers — prior Hinglish NLP work, sentiment analysis surveys, MuRIL paper

- Dataset: Describe SemEval 2020 Task 9 — size, labels, source, class distribution (show your EDA figure here)

- Methodology: Describe each model with equations for classical models, architecture diagram for LSTM, fine-tuning setup for MuRIL

- Experiments: Preprocessing steps, hyperparameters used, hardware setup, evaluation metrics chosen

- Results: Comparison table + confusion matrices + bar chart. State which model wins and by how much

- Error Analysis: Pick 10-15 misclassified examples and explain WHY the model got them wrong

- Conclusion: Summarize findings, limitations, future work (2-3 sentences each)

# 8. Important Tips for First-Time Researchers

- Keep every experiment reproducible — set random seeds at the top of every file (random.seed(42), np.random.seed(42), torch.manual_seed(42))

- Save all metrics to a JSON file from day one — do not rely on notebook outputs which get lost

- Write your paper alongside your experiments, not after — update the methodology section as you build each model

- Never fabricate or cherry-pick results — report all numbers honestly, including when a model performs poorly

- Your professor will likely ask you to improve one thing before submission — build in buffer time in Week 9

- When submitting, choose ONE venue — do not submit to multiple places simultaneously (it violates academic ethics)

- Cite every dataset, pretrained model, and library you use — including the MuRIL paper and SemEval dataset paper

Prepared for: B.Tech Research Mentorship

Good luck with your research. Work honestly, and the publication will follow.